## ProductBacklog
ID | As a | I want to | so that | Dependencies | Complexity | Value | Priority | Done?
1 | Administrator | Be able to add a new problem to the System | users can update their app to incorporate the new items | 3 | 1 | 100 | 100 | Yes
2 | Administrator | Be able to delete a problem from the System | users can update their app to delete obsolete or faulty items | 3 | 1 | 70 | 70 | Yes
3 | Administrator | Be able to edit a problem in the System | users can update their app to include changes in knowledge |  | 3 | 70 | 210 | Yes
| Administrator | Be able to add a new symptom to the system | users can diagnose their current problem faster |  | 1 | 70 | 80 | Yes
| Administrator | Be able to delete a symtom from the system | users can update there app to delete obsolete or faulty items |  | 1 | 70 | 80 | Yes
| Administrator | Be able to edit a symptom on the system | users can update their app to include changes in knowledge |  | 1 | 70 | 80 | Yes
4 | Administrator | Be able to define a menu structure which enables the user to navigate to content easily | the search time is minimal and ideally logarithmicaly related to the size of the data set available |  | 2 | 100 | 200 | No
5 | User | Be able to navigate through a menu structure to diagnose my problem | I can find the advice I need in the application data |  | 1 | 50 | 50 | No
6 | User | Be able to find further information on a subject | I can further educate myself if the information in the application is insufficient |  | 1 | 100 | 100 | No
7 | User | Be able to check for updates and update the application | I can benefit from the latest updates and additions to the database |  | 3 | 100 | 300 | No
8 | Developer | Be able to scale the application to future growth and research | the application can be kept up to date throughout time |  | 4 | 100 | 400 | No
9 | Developer | be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates | only the new data is downloaded in a update. |  | 4 | 50 | 200 | No
10 | Developer | be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data | future updates don't interfere with the application design and allow long term scalability |  | 4 | 150 | 600 | No
11 | Developer | be able to create a functional relational database | I can store necessary data used for the app |  | 4 | 150 | 600 | Yes
12
13
14
15
16

## Sprint Backlog
Sprint Backlog | Sprint 0
Sprint Backlog | Estimated Effort (person hours) | Team Member Responsible | Current Status | Comments | Daily Update
[5 empty] | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
[5 empty] | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03
As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items |  |  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Design Database | 5 | KM | Complete |  | 5 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
Create Database tables | 5 | KM | Complete |  | 5 | 3 | 8 | 5 | 2 | 8 | 8 | 6 | 4 | 3 | 0 | 0 | 0
populate DB | 15 | KM | Complete |  | 15 | 15 | 8 | 6 | 5 | 3 | 4 | 5 | 3 | 0 | 0 | 0 | 0
Create Stored Procedures | 9 | KM | Complete |  | 9 | 9 | 4 | 5 | 3 | 5 | 7 | 3 | 4 | 2 | 0 | 0 | 0
Create Website that connects to Database | 30 | KM, TB | Complete |  | 30 | 25 | 4 | 8 | 3 | 9 | 7 | 9 | 9 | 5 | 3 | 0 | 0
Create webform with ability to add to the database | 1 | KM, TB | Complete |  | 1 | 1 | 4 | 7 | 6 | 8 | 8 | 9 | 9 | 4 | 4 | 0 | 0
As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items |  | KM, TB | Complete
Create webform with ability to delete from the database | 1 | KM, TB | Complete |  | 1 | 1 | 8 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system |  | KM, TB | Complete
Create webform with ability to edit the database | 1 | KM, TB | Complete |  | 1 | 1 | 8 | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proporationate to the data size. |  | SL
Design XML protocol structure | 5 | TB | Complete |  | 5 | 4 | 8 | 7 | 4 | 5 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Implement Database to XML converter | 10 | TB | Complete |  | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
As a User, I want to be able to navigate through a menu structure to diagnose my probem so that I can find the advice I need within the application |  | RS,SL
Create Android Application Shell | 1 | RS,SL | Complete |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Frame for Menu | 2 | RS,SL | Complete |  | 2 | 2 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Content Page for Diseases | 2 | RS,SL | Complete |  | 2 | 2 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient
Format urls and links in data to work as hyperlinks within application | 2 | RS,SL | Complete |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database.
Include update button in application | 1 | RS,SL | Complete |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Include functionality in Database so that every row has a timestamp | 2 | RS,SL,KM,TB | Complete |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Include a comparing functionality which enables the comparison between the user app status timestamp and the data timestamp to determine which data has to be updated | 2 | RS,SL,KM,TB | Complete |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a Developer, I want to be able to scale the application to future growth and reasearch so that the appliaction can be kept up to date throughout time.
Design and write the application XML parser | 10 | TB | Complete |  | 10 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 2 | 1 | 0 | 0 | 0
Write a script which creates the Application GUI dynamically from XML | 10 | TB | Complete |  | 10 | 10 | 10 | 7 | 5 | 5 | 3 | 1 | 3 | 0 | 0 | 0 | 0
As a Developer, I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update
Add a timestamp to every item on both the user side and the client side of the application | 5 | KM, TB | Complete |  | 5 | 5 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability
Create dynamic content creation from XML source uppon update | 10 | TB | Complete |  | 10 | 9 | 9 | 7 | 6 | 4 | 4 | 5 | 4 | 2 | 0 | 0 | 0
|  |  |  | Hours Remaining | 129 | 115 | 117 | 102 | 75 | 72 | 70 | 61 | 52 | 22 | 7 | 0 | 0
|  |  |  | (Difference from Yesterday) |  | 14 | -2 | 15 | 27 | 3 | 2 | 9 | 9 | 30 | 15 | 7 | 0
Total Estimated Effort this sprint | 129 | hours
Progress Breakdown
Tasks Remaining | 0
Tasks in Progress | 0
Tasks Complete | 23

## Acceptance Tests
User Story | Acceptance Test | Accepted? | Comments
“As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a web app, User can add new problems and symptoms, Database is populated with new data |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a web app, User can delete selected problems and symptoms, Database is updated with deleted field |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a web app, User can edit selected problems and symptoms, User is taken to edit page, Fields are populated with current information about the problem, Database is updated with new data field |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proportionate to the data size.” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a SDK app, XML protocol successfully converts data into a package |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a User, I want to be able to navigate through a menu structure to diagnose my problem so that I can find the advice I need within the application.” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a SDK app, User can navigate through the menu system fast, Allocated memory allows a fast navigation system |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient.” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a SDK app, User can navigate through the menu system that displays different symptoms, User can diagnose their potato problem |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient.” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a SDK app, User can navigate through the menu system that displays different symptoms, User can diagnose their potato problem |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database.” | Application of a whole compiles, free of errors, Code compiles and application can be ran as a SDK app, User can download updates using the download button on the main menu to update the app, App compares current version number to new version number within the database, App downloads new data applying the version number |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a Developer, I want to be able to scale the application to future growth and research so that the application can be kept up to date throughout time.” | Application updates successfully through application xml parsing |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a Developer, I want to be able to update the user application where changes occurred, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in an update” | Application updates successfully through application xml parsing, Application new data download is compared with the databases current date stamp and the applications database current time stamp successfully |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
“As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability” | Application downloadable dynamic XML content successfully updates |  | The testing should continue providing that all the acceptance tests have been passed and approved by the client
Comments for next Sprint:

## user_stories
User Stories
As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items
As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items
As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system
As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proporationate to the data size.
As a User, I want to be able to navigate through a menu structure to diagnose my probem so that I can find the advice I need within the application
As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient
As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database.
As a Developer, I want to be able to scale the application to future growth and reasearch so that the appliaction can be kept up to date throughout time.
As a Developer, I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update
As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability

## UserStories
10. As a Developer I want to Be able to scale the application to future growth and research so that the application can be kept up to date throughout time Complexity: 4 Value: 100 Priority: 400
13. As a I want to so that Complexity: Value: Priority: 0
12. As a Developer I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update. Complexity: 4 Value: 50 Priority: 200
2. As a Administrator I want to Be able to delete a problem from the System so that users can update their app to delete obsolete or faulty items Complexity: 1 Value: 70 Priority: 70
#REF!
7. As a User I want to Be able to find further information on a subject so that I can further educate myself if the information in the application is insufficient Complexity: 1 Value: 100 Priority: 100
6. As a User I want to Be able to navigate through a menu structure to diagnose my problem so that I can find the advice I need in the application data Complexity: 1 Value: 50 Priority: 50
8. As a User I want to Be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database Complexity: 3 Value: 100 Priority: 300
3. As a Administrator I want to Be able to define a menu structure which enables the user to navigate to content easily so that the search time is minimal and ideally logarithmicaly related to the size of the data set available Complexity: 3 Value: 70 Priority: 210
14. As a I want to so that Complexity: Value: Priority: 0
15. As a I want to so that Complexity: Value: Priority: 0
1. As a Administrator I want to Be able to add a new problem to the System so that users can update their app to incorporate the new items Complexity: 1 Value: 100 Priority: 100
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0

## Configuration Details
Sprint Start Date | 2014-09-17
Team Member Codes
N/A | NOT ASSIGNED
SL | Stephanie Lee
TB | Thomas Butterworth
KM | Kurtis Mulgrew
RS | Ron Schoenberg
KM, TB
RS,SL
RS,SL,KM,TB
TB