## ProductBacklog
ID | As a | I want to | so that | Dependencies | Complexity | Value | Priority | Done?
1 | Administrator | Be able to add a new problem to the System | users can update their app to incorporate the new items | 3 | 1 | 100 | 100 | Yes
2 | Administrator | Be able to delete a problem from the System | users can update their app to delete obsolete or faulty items | 3 | 1 | 70 | 70 | Yes
3 | Administrator | Be able to edit a problem in the System | users can update their app to include changes in knowledge |  | 3 | 70 | 210 | Yes
| Administrator | Be able to add a new symptom to the system | users can diagnose their current problem faster |  | 1 | 70 | 80 | Yes
| Administrator | Be able to delete a symtom from the system | users can update there app to delete obsolete or faulty items |  | 1 | 70 | 80 | Yes
| Administrator | Be able to edit a symptom on the system | users can update their app to include changes in knowledge |  | 1 | 70 | 80 | Yes
4 | Administrator | Be able to define a menu structure which enables the user to navigate to content easily | the search time is minimal and ideally logarithmicaly related to the size of the data set available |  | 2 | 100 | 200 | No
5 | User | Be able to navigate through a menu structure to diagnose my problem | I can find the advice I need in the application data |  | 1 | 50 | 50 | No
6 | User | Be able to find further information on a subject | I can further educate myself if the information in the application is insufficient |  | 1 | 100 | 100 | No
7 | User | Be able to check for updates and update the application | I can benefit from the latest updates and additions to the database |  | 3 | 100 | 300 | No
8 | Developer | Be able to scale the application to future growth and research | the application can be kept up to date throughout time |  | 4 | 100 | 400 | No
9 | Developer | be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates | only the new data is downloaded in a update. |  | 4 | 50 | 200 | No
10 | Developer | be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data | future updates don't interfere with the application design and allow long term scalability |  | 4 | 150 | 600 | No
11 | Developer | be able to create a functional relational database | I can store necessary data used for the app |  | 4 | 150 | 600 | Yes
12
13
14
15
16

## Sprint Backlog
Sprint Backlog | Sprint 0
Sprint Backlog | Estimated Effort (person hours) | Team Member Responsible | Current Status | Comments | Daily Update
[5 empty] | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
[5 empty] | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03
As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items |  |  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Design Database | 5 | KM | Complete |  | 5 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Create Database tables | 5 | KM | Complete |  | 5 | 3 | 8 | 5 | 2 | 8 | 8 | 6 | 4
populate DB | 15 | KM | Complete |  | 15 | 15 | 8 | 6 | 5 | 3 | 4 | 5 | 3
Create Stored Procedures | 9 | KM | Complete |  | 9 | 9 | 4 | 5 |  | 5 | 7 | 3 | 4
Create Website that connects to Database | 30 | KM, TB | Complete |  | 30 | 25 | 4 | 8 | 3 | 9 | 7 | 9 | 9
Create webform with ability to add to the database | 1 | KM, TB | Complete |  | 1 | 1 | 4 | 7 | 6 | 8 | 8 | 9 | 9
As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items |  | KM, TB | Complete
Create webform with ability to delete from the database | 1 | KM, TB | Complete |  | 1 | 1 | 8 | 3 | 1 | 1 | 1 | 1 | 1
As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system |  | KM, TB | Complete
Create webform with ability to edit the database | 1 | KM, TB | Complete |  | 1 | 1 | 8 | 5 | 1 | 1 | 1 | 1 | 1
As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proporationate to the data size. |  | SL
Design XML protocol structure | 5 | TB | Complete |  | 5 | 4 | 8 | 7 | 4 | 5 | 6 | 4 | 2
Implement Database to XML converter | 10 | TB | In Progress |  | 2014-09-17: 10; 2014-09-18: 10
As a User, I want to be able to navigate through a menu structure to diagnose my probem so that I can find the advice I need within the application |  | RS,SL
Create Android Application Shell | 1 | RS,SL | Complete |  | 2014-09-17: 1; 2014-09-18: 1; 2014-09-19: 0
Create Frame for Menu | 2 | RS,SL | Complete |  | 2014-09-17: 2; 2014-09-18: 2
Create Content Page for Diseases | 2 | RS,SL | In Progress |  | 2014-09-17: 2; 2014-09-18: 2
As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient
Format urls and links in data to work as hyperlinks within application | 2 | RS,SL | In Progress |  | 2014-09-17: 2; 2014-09-18: 2
As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database.
Include update button in application | 1 | RS,SL | In Progress | bar: 2014-09-17 to 2014-09-18
Include functionality in Database so that every row has a timestamp | 2 | RS,SL,KM,TB | In Progress |  | 2014-09-17: 2; 2014-09-18: 2
Include a comparing functionality which enables the comparison between the user app status timestamp and the data timestamp to determine which data has to be updated | 2 | RS,SL,KM,TB | Not Started |  | 2014-09-17: 2; 2014-09-18: 2
As a Developer, I want to be able to scale the application to future growth and reasearch so that the appliaction can be kept up to date throughout time.
Design and write the application XML parser | 10 | TB | In Progress |  | 2014-09-17: 10; 2014-09-18: 8
Write a script which creates the Application GUI dynamically from XML | 10 | TB | Not Started |  | 2014-09-17: 10; 2014-09-18: 10
As a Developer, I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update
Add a timestamp to every item on both the user side and the client side of the application | 5 | KM, TB | Not Started |  | 2014-09-17: 5; 2014-09-18: 5
As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability
Create dynamic content creation from XML source uppon update | 10 | TB | In Progress |  | 2014-09-17: 10; 2014-09-18: 9
|  |  |  | Hours Remaining | 129 | 115 | 60 | 54 | 30 | 48 | 50 | 46 | 41 | 0 | 0 | 0 | 0
|  |  |  | (Difference from Yesterday) |  | 14 | 55 | 6 | 24 | -18 | -2 | 4 | 5 | 41 | 0 | 0 | 0
Total Estimated Effort this sprint | 129 | hours
Progress Breakdown
Tasks Remaining | 3
Tasks in Progress | 7
Tasks Complete | 13

## Acceptance Tests
User Story | Acceptance Test | Accepted? | Comments
As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items | The administrator can add new items to the database. When checking for updates, the user is prompted to synchronize the latest changes.
As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items | The administrator can delete a item from the database. When checking for updates, the user is prompted to synchronize the latest changes which will also delete marked items.
As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system | The administrator can edit a item in the database. When checking for updates, the user is prompted to synchronize the latest changes which will also change the edited items as they will have a later timestamp.
As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proporationate to the data size. | The administrator can define the menu path for a item and thereby define the menu structure. It is also possible to have multiple paths for a item, enabling a search for a item by different symptoms.
As a User, I want to be able to navigate through a menu structure to diagnose my probem so that I can find the advice I need within the application | The user can filter the data set and define the granularity of the data presented until the requested item is found in the application. Since each submenu can have several further submenus, the data set can be enormous, with only few submenus to eliminate invalid responses.
As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient | The user can find links to further information within the information page.
As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database. | The user can check for updates via the main menu screen and start the download of the update if there is a newer version available.
As a Developer, I want to be able to scale the application to future growth and research so that the appliaction can be kept up to date throughout time. | Because of the very broad search criteria in the menu, it is possibel for the user to select a narrow choice of items from a potentially very large data set. This means that, even though the current data sets hardly exceeds 20, the navigation for 100 items will not be any more difficult and chosing the correct item will not take more time.
As a Developer, I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update. | Each item has a timestamp which is hidden from the user, which indicates whether the item was added prior of after the user downloaded data the last time. The user then only downloads the data which is not already on the user smartphone and therefore saves a lot of time and data traffic.
As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability | THe user interface is built automatically after a update and therefore a perfect match of the databases model of the data. The design is item-oriented and with the dynamic creation of the menu path, adapts to any changes instantly without leaving any traces of former items or designs which could depreciate the user experience.
Comments for next Sprint:

## user_stories
User Stories
As an Administrator, I want to be able to add items to the system so that users can update their app to incorporate new items
As an Administrator, I want to be able to delete items from the system so that users can update their app to delete faulty or obsolete items
As an Administrator, I want to be able to edit content in the system so that users can update their app to include changes made to the system
As an Administrator, I want to be able to define a menu structure which enables the user to navigate the content easily so that the search time is minimized and ideally logarithmically proporationate to the data size.
As a User, I want to be able to navigate through a menu structure to diagnose my probem so that I can find the advice I need within the application
As a User, I want to be able to find further information on the subject so that I can further educate myself if the information in the application is insufficient
As a User, I want to be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database.
As a Developer, I want to be able to scale the application to future growth and reasearch so that the appliaction can be kept up to date throughout time.
As a Developer, I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update
As a Developer, I want to be able to create a dynamically synchronized user interface which adapts to the data structure of the downloaded data so that future changes don't interfere with the application design and allow long term scalability

## UserStories
10. As a Developer I want to Be able to scale the application to future growth and research so that the application can be kept up to date throughout time Complexity: 4 Value: 100 Priority: 400
13. As a I want to so that Complexity: Value: Priority: 0
12. As a Developer I want to be able to update the user application where changes occured, avoiding a complete download of all the data and enabling selective updates so that only the new data is downloaded in a update. Complexity: 4 Value: 50 Priority: 200
2. As a Administrator I want to Be able to delete a problem from the System so that users can update their app to delete obsolete or faulty items Complexity: 1 Value: 70 Priority: 70
#REF!
7. As a User I want to Be able to find further information on a subject so that I can further educate myself if the information in the application is insufficient Complexity: 1 Value: 100 Priority: 100
6. As a User I want to Be able to navigate through a menu structure to diagnose my problem so that I can find the advice I need in the application data Complexity: 1 Value: 50 Priority: 50
8. As a User I want to Be able to check for updates and update the application so that I can benefit from the latest updates and additions to the database Complexity: 3 Value: 100 Priority: 300
3. As a Administrator I want to Be able to define a menu structure which enables the user to navigate to content easily so that the search time is minimal and ideally logarithmicaly related to the size of the data set available Complexity: 3 Value: 70 Priority: 210
14. As a I want to so that Complexity: Value: Priority: 0
15. As a I want to so that Complexity: Value: Priority: 0
1. As a Administrator I want to Be able to add a new problem to the System so that users can update their app to incorporate the new items Complexity: 1 Value: 100 Priority: 100
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0
. As a I want to so that Complexity: Value: Priority: 0

## Configuration Details
Sprint Start Date | 2014-09-17
Team Member Codes
N/A | NOT ASSIGNED
SL | Stephanie Lee
TB | Thomas Butterworth
KM | Kurtis Mulgrew
RS | Ron Schoenberg
KM, TB
RS,SL
RS,SL,KM,TB
TB